## Slide 1
50 Governing Board
Item 13
Jūrmala, (Latvia), June 2019
Thank you for your attention!
Tribunal de Cuentas de España – EUROSAI Secretariat
Item 5.3.
Communication Portfolio
58th EUROSAI Governing Board meeting
Vilnius (Lithuania) 14 – 15 June 2023
- EUROSAI Secretariat

## Slide 2
SAI of Spain (EUROSAI Secretariat)
Leader of the Portfolio
SAI of Israel (1st Vice-Presidency of EUROSAI)
Co-leader of the Portfolio
COMMUNICATION PORTFOLIO – LEADERS
ESP 2017-2024
Guiding principle 3
“To promote increased member participation and extend the value of EUROSAI’s activities among its members and other stakeholders through enhanced communications”

## Slide 3
Guidelines for implementing an effective and enhanced communication in EUROSAI (Communication Framework)
COMMUNICATION PORTFOLIO – MAIN PROJECTS
  Formal procedure for the distribution and publicity of the results of the work carried out by the SGs, PGs, WGs & TFs to EUROSAI members
  Information procedure that takes place after the Congresses and GBs

1. Development of the Communication Framework

## Slide 4
  Answers until 15/03/2023: 5 companies answered
  Analysis of the responses by Secretariat & TIC
  One excluded due to technical issues and excessive budget
COMMUNICATION PORTFOLIO – MAIN PROJECTS
EUROSAI activities and products more visible and accessible to the Organisation's members and stakeholders; reach out to all the EUROSAI community and encourage active participation
Market research published 28/02/2023
2. PG for the “Relaunch of EUROSAI’s website”

## Slide 5
COMMUNICATION PORTFOLIO – MAIN PROJECTS
2. PG for the “Relaunch of EUROSAI’s website”
COMPARISON CHART- DEVELOPMENT & EXPLOITATION
VAT EXCLUDED
SUPPLIER 1 | SUPPLIER 3 | SUPPLIER 4 | SUPPLIER 5
170.114,40 | 172.681,81 | 212.640,00 | 125.740,90*
(*) Total figure provided by Supplier no. 5 does not coincide with breakdown
(More information in the Secretariat’s report on the results of the market consultation)

## Slide 6
COMMUNICATION PORTFOLIO – MAIN PROJECTS
2. PG for the “Relaunch of EUROSAI’s website”
STIC Directorate’s main conclusions:
Pre-offers are usually higher in price than final price
Additionally, they consider the effort (hours) may be lesser
With these in mind, they estimated an average of EUR 157,000, VAT Excluded
Once a web is launched, actualisations around every two years should be taken into consideration. They should be contracted separately, and the estimation of each is around 15% of the initial development
Submitted to GB for written approval
To be considered when drafting next budgets

## Slide 7
COMMUNICATION PORTFOLIO – MAIN PROJECTS
2. PG for the “Relaunch of EUROSAI’s website”
Technical & economic docs (ITC)
- Review & administrative docs (Procurement)
- Approval TCE’s GC
- Tender procedure: Publication (Procurement)
- Adjudication
- START

## Slide 8
3. Management and update of the current EUROSAI website
COMMUNICATION PORTFOLIO – MAIN PROJECTS
Project Groups’ section update:
Status
Outputs

Notes: constant updating of the contents of the website

## Slide 9
No. 27
  Proposed theme: "SAIs: in search of citizens' engagement"
  Call for contributions in December 2022
  Deadline: 31/01/2023 (extended to 30/04/2023)
  Estimated launch: Summer 2023
COMMUNICATION PORTFOLIO – MAIN PROJECTS
Regular publication
Responsible: SAI Israel (Newsletter design, calls for topics, etc.)
It can be news from SAIs and INTOSAI, not only from EUROSAI
To be launched by June 2023
4. EUROSAI Magazine
5. EUROSAI Highlights Newsletter

## Slide 10
6. EUROSAI YouTube channel
COMMUNICATION PORTFOLIO – MAIN PROJECTS
Responsible SAI: Israel
Twitter, blogging sites, Wikipedia, etc.
  EUROSAI Presidency Social media:
  Presidency website: www.eurosai2021.cz
  Official Twitter account: EUROSAI Presidency @EUROSAI_OP
New Governing Board members (available)
New EUROSAI First Vice-Presidency (available)
New Heads of SAIs (available)

7. Social media and other tools with the EUROSAI's contents
8. EUROSAI Welcome packages to newcomers


## Slide 11
Package with presentations (EUROSAI at a glance), videos, PPTs, leaflet... of EUROSAI activities and outputs, mostly aimed for auditors (to be disseminated within SAIs)
Videos, PPTs, leaflet of EUROSAI activities
and outputs, mostly aimed for auditors
(Responsible parties TBD)
Video at the EUROSAI booth at INCOSAI
Easy and accessible resources to communicate (to make easy and user-friendly surveys; to create modern PPTs, ...) (Responsible parties TBD)
e.g.: INTOSAI – DONOR COOPERATION
COMMUNICATION PORTFOLIO – MAIN PROJECTS
9. Promotion of EUROSAI within member SAIs - "Communication Package"

10. Resource Kit for an enhanced communication

## Slide 12
Thank you for your attention!
58th EUROSAI Governing Board meeting
Vilnius (Lithuania) 14 – 15 June 2023